SOP

Annual HR Strategy Planning SOP

Strategic HR Leadership   |   SOP   |   Version 1.0   |   [Organization Name]

1. Purpose

This SOP runs the annual cycle that turns the business plan into an approved, budgeted HR strategy in about ten weeks.

2. Procedure

| Step | Action | Responsible | Timeline | Output |
| --- | --- | --- | --- | --- |
| 1 | Collect inputs: business plan, growth targets, restructures, market and regulatory changes. | Head of HR | Weeks 1–2 | Input pack |
| 2 | Analyze the workforce: capability gaps, risks, succession, engagement, turnover. | HR Analytics / HRBPs | Weeks 2–4 | Workforce analysis |
| 3 | Draft 3–5 strategic HR priorities linked to business priorities. | HR Leadership Team | Weeks 4–6 | Draft strategy |
| 4 | Cost the plan: budget, headcount, systems; test with Finance. | Head of HR / Finance | Weeks 6–7 | Budgeted plan |
| 5 | Executive approval of strategy, budget, and success measures. | Executive Team | Week 8 | Approved strategy |
| 6 | Cascade: each HR sub-function writes its annual plan; all-staff communication. | HR Leadership Team | Weeks 9–10 | Function plans |
| 7 | Quarterly scorecard reviews; adjust priorities when conditions change. | Head of HR / Executives | Quarterly | Review minutes |

3. Approvals

- Strategy, budget, and headcount: executive team sign-off each year.

- Mid-year re-prioritization with budget impact: CEO approval.

4. Escalation

If business results threaten the HR budget mid-year, the Head of HR presents reprioritization options to the executive team within ten working days.